## Slide 1: FLOOD_AID
Preparation of aid worker teams to be deployed in the Hungarian-Romanian floodplain
Agreement no. ECHO/SUB/2013/671449

## Slide 3: Project area and pilot villages
Gulács
Dumbravita
Turulung

## Slide 5: The Problem:
Upper floodplain of the Tisza-Mures:
High and increasing flooding risk
Transnational territory
  different legislation, regulations and administrative set-up
  different official languages
Long tradition of working together in emergencies, but
  need for civil society to efficiently support official disaster management structures
  NGOs lack capacity and means
  weak awareness of modern approaches in disaster management/prevention

## Slide 6: The proposed solution (aim of the project):
To train and equip a Hungarian-Romanian volunteer aid worker team, able to provide rapid response in support to official disaster management authorities
To provide effective guidance to communities at risk, enhancing their ability to react and mitigate the effects of disasters.

## Slide 7
Trained volunteer aid-worker team
Develop and translate curriculum
By June 2014
Hold 80-hour training course for 40 volunteers
By January 2015
Local intervention plans in 3 pilot villages
Conduct risk assessments
By June 2014
Complete family emergency plans
By October 2014
Equipment purchase
By August 2014
Purchase of drying aggregators
Train teams to use new equipment
Hold joint field exercises
By May 2015
Train local volunteers
By July 2014
Purchase of tents
Purchase of other equipment
Project outputs
and summarised activities

## Slide 8: Proposed training curriculum:
Introduction to disasters
Coordination-cooperation, legal environment, human rights approach
Rapid assessments, situation analysis
Project design
Psycho-social interventions
Safety, security, first aid
Administration, data protection , Sphere
Disaster risk reduction

## Slide 9: Cross-cutting outputs
Communication and publicity
Communication with stakeholders
Management and reporting
Day-to-day management
Monitoring and reporting
Awareness-raising
Publicity and dissemination of results
Elaboration of case study

## Slide 10: Project structure
HCSOM (NGO, Hungary) - coordinator
Gulács municipality (LA, Hungary)
Caritas Satu Mare (NGO, Romania)
SAMR Baia Mare (NGO, Romania) – beneficiaries
Turulung municipality (Satu Mare) (LA, Romania)
Dumbravita municipality (Baia Mare) (LA, Romania)
- associates
Total budget (over 21 months): € 264,696

## Slide 11: Continuation
Partners will maintain a long-term institutional cooperation. Formal arrangements will be made for sharing the equipment among all when needed. N.B. 3 of the 4 partners employ a permanent civil protection specialist.
The cross-border team will be kept operational and replenished. Further joint training and exercises will be undertaken regularly.
The local emergency planning and volunteer training done in the 3 pilot villages will be scaled up as appropriate.
Achievements and lessons learnt will be disseminated for wider application by other municipalities and NGOs of the sub-region.