## Slide 1: EUROWA Module
European Module for Oiled Wildlife Emergency Response Assistance

## Slide 2: Project facts
Build a Module (experts and their equipment) for oiled wildlife response
24 months duration
5 partners
Total eligible costs: € 410,821
EC Contribution (75%): € 304,946

## Slide 3: Partners and beneficiaries
Coordination
  Sea Alarm
Partners
  Wildlife Rescue Centre Ostend (WRCO)-Belgium
  Royal Society for the Prevention of Cruelty to Animals (RSPCA)- UK
  World Wide Fund for Nature, Finland (WWF-Finland) - FI
  ProBird-DE
Subcontractors
  Estonia Fund for Nature - EE
  ONIRIS – Veterinary School Nantes - FR

## Slide 4: Backgrounds
Past experience
Incidental marine oil spills may affect wildlife
  Hundreds to thousands animals may be affected in the course of days
  Public interested in saving animals
  Professional expertise needed, but often not locally available
Trends
Increasing density of maritime traffic
Governments looking for integration of wildlife response into oil spill preparedness
Mutual assistance for wildlife response as part of regional agreements
Professional wildlife response knowledge and tools increasingly available

## Slide 5: Objectives
Developing a Standard Operating Procedure (SOP) for Module
Developing a professional training course for Module functions
Providing the training course to European individuals
Maintain equipment and prepare for its mobilisation
Test the module via an international exercise
Submit the Module for registration in CECIS

## Slide 6: Tasks and actions (A - H)
Task ID | Task Title | Start Date | End Date | Actions
A | Project management and reporting to the commission | 1 January 2015 | 31 December 2016 | A1 – Project technical and financial Coordination A2 – Kick-off meeting A3 – Second monitoring meeting A4 – Progress and final reports preparation A5 – Analysis of evaluation sheets and feedback from participants
B | Communications | 1 January 2015 | 31 December 2016 | B1 – Project website in www.oiledwildlife.eu B2 – Project promotion in relevant events B3 – Newsletter/layman/s report
C | SOP development | 1 February 2015 | 31 December 2016 | C1 – Project Workshop C2 – Develop draft SOP C3 – Final SOP after evaluation project results C4 – Database with details on people and equipment
D | Training curriculum and course development | 1 March 2015 | 1 July 2016 | D1 – Veterinarian Training package development D2 – Facility manager training package D3 – Animal Care expert training package D4 – Advanced Volunteer training package D5 – E-learning package on tiered oiled wildlife response D6 – Proposed accreditation guidelines

## Slide 7: Tasks and actions (A - H)
Task ID | Task Title | Start Date | End Date | Actions
E | Equipment inspection, management and handbook | 1 May 2015 | 1 Nov 2016 | E1 – Equipment inspection and maintenance in 2015 E2 – Equipment inspection and maintenance in 2016 E3 – Equipment handbook development
F | Training events | 1 Oct 2015 | 1 Dec 2016 | F1 – Veterinarian & facility manager training event F2 – Animal Care expert training event F3 – Advanced Volunteer training event F4 – Team member training event 1 F5 – Team member training event 2
G | Exercises | 1 October 2015 | 1 Oct 2016 | G1 - Equipment mobilisation exercise G2 - Team mobilisation exercise (table top) G3 - Team mobilisation exercise (field exercise)
H | Package material publication | 1 January 2016 | 31 December 2016 | H1 – Package design and specification H2 - Preparation of the high definition PDF format for paper publication H3 – Printing and reproduction

## Slide 8: Deliverables (A – H)
A | Meeting and progress reports
B | Webpage, News articles, Advocacy, Layman’s report
C | Standard Operational Procedure, Database
D | Training packages, e-learning package, proposal on accreditation
E | Equipment pack list and hand book
F | 5 training events, ~ 35 certified experts
G | Exercises (equipment mobilisation, team mobilisation table top, module mobilisation field exercise)
H | Printed SOP, Printed training materials, Printed Layman’s Report

## Slide 9: Follow-up
Registration of Module in CESIS
Continued training of Module experts
(Basic) training of wildlife responders in each coastal EU Member State
Module’s 24/7 readiness (via BE/Sea Alarm)
Integration of Module into other systems of preparedness (e.g. industry)