## Slide 1
MATILDA Project
Bruxelles, 20 January 2015
Kick off meeting for the selected projects under the 2014
Call for proposals for prevention and preparedness projects

## Slide 2
ACRONYM: MATILDA
PrOJECT Name:
MultinATIonal moduLe on Damage Assessment and countermeasures
FRAMEWORK:
CALL FOR PROPOSALS 2014 FOR PREVENTION AND PREPAREDNESS PROJECTS IN CIVIL PROTECTION AND MARINE POLLUTION. PREPAREDNESS PRIORITIES: ACTION 2
STARTING DATE: 1 JANUARY 2015
DURATION: 24 months
THE Project

## Slide 3
The Matilda project is focused on the design and implementation of a multinational macro-module for post-earthquake building safety assessment and countermeasures in international emergencies.
The macro-module is based on the experience developed within the DrHouse project, funded by the European Commission under the "Preparatory Action on an EU Rapid Response Capability". Main result of DrHouse project was the design, implementation, training and exercising of the Build-Safe macro-module.
While Build-Safe entirely consists of Italian resources (Civil Protection Department, Eucentre, Fire Department, Italian Regions), Matilda project is intended to provide the multinational dimension to the macro-module.
DESCRIPTION OF THE Project

## Slide 4
    3 Countries: ITALY, SLOVENIA, CROATIA
    5 Partners:
    Presidency of the Council of Ministers-Italian Civil Protection Department (CPD), Italy (IT)-COORDINATOR
    Administration for Civil Protection and Disaster Relief, Slovenia (SI)
    National Protection and Rescue Directorate, Croatia (HR)
    Italian Fire Rescue Service (VVF), Italy (IT)
    European Centre for Training and Research in Earthquake Engineering (EUCENTRE), Italy (IT)
Cost of the Project: 666,599,30 EUR
EU Financial Contribution : 499,949,30 EUR
(75% total eligible costs)
INFORMATION ON THE Project
  Partecipants

## Slide 5
Task A. Project Management and Reporting
Task B. Making Build-Safe Multinational, dedicated to the design and implementation of the multinational module and to define the Standard Operative Procedures
Task C. Training, to improve both technical skills and participation in international emergencies
Task D. Small scale exercise, to test the deployment and the on-site operational capabilities
Task E. Dissemination, to implement the valorisation plan, including lessons learned
Project TASKS
Task and Actions

## Slide 6
Task A. Management and Reporting
Technical and administrative management (intermediate and final report, audit, meeting with the Commission, ..)
Actions
Action A.1. Overall management
Action A.2. Technical management
Action A.3. Administrative management
Action A.4. Financial management
Action A.5. Monitoring and feedback on the project
TASK a-ACTIONS

## Slide 7
Task A. Management and Reporting
Deliverables
D.A.1. Interim progress reports at 1/3 of the project
D.A.2. Interim progress reports at 2/3 of the project
D.A.3. Final report
TASK a-dELIVERABLES

## Slide 8
Task B. Making Build-Safe multinational
How to extend the existing Build-Safe macro-module into a multinational module.
Actions
Action B.1.Defining the Build Safe multinational module
  Action B.2. Building multinational integration in the team
  Action B.3. Establishing standard operative procedures
  for activation, deployment, operational and financial issues in a multinational team.
TASK b-ACTIONS

## Slide 9
Deliverables
D.B.1. Start-up configuration of the multinational module (identification of required skills and expertise, identification of team members for each MS, logistic)
D.B.2. Standard operative procedures for activation, deployment, operational and financial issues in a multinational team
D.B.3. Development of common administrative and financial procedures to manage a multinational module
D.B.4. Establishment of a common lexicon for the experts
D.B.5. Development of a specific format/information sheet for the requesting Country
TASK B-DELIVERABLES
Task B. Making Build-Safe multinational

## Slide 10
Task C. Training
Actions
5 Training courses for a total of about 100 trainees
Action C.1. 2 Basic training courses on damage assessment (Place tbf)
Action C.2. 1 Advanced training course on experimental test and procedures of damage assessment (Pavia, IT)
Action C.3. 2 Training courses on Short Term Countermeasures (Ljubljana, SI)
TASK C-ACTIONS

## Slide 11
Task C. Training
Deliverables
D.C.1. BSA training courses and report
D.C.2. ASA training courses and report
D.C.3. STC training course and report
TASK C-DELIVERABLES

## Slide 12
Task D. Small scale exercise
A small scale exercise (3 days-long plus travel time) on damage assessment and countermeasures for the deployment of a multinational module based on a realistic scenario will be designed based on a realistic scenario with participants and observers from the countries involved in the Project and other MS, including a one-day evaluation with the Commission
Actions
Action D.1. Design of a small scale exercise
Action D.2. Implementation of the exercise
(place: tbf, date: October 2016)
TASK D-ACTIONS

## Slide 13
Task D. Small scale exercise
Deliverables
D.D.1. Report on the design of a small scale exercise
D.D.2. Implementation of the small scale exercise
D.D.3. Exercise evaluation and lessons learned report
TASK D-DELIVERABLES

## Slide 14
Task E. Dissemination
Dissemination, visibility and valorisation of the project and the EU Civil Protection Mechanism
Actions
Action E.1. Web portal
Action E.2. Production of e-brochures and advertising material
Action E.3. Media work and video clip
Action E.4. Layman’s Report
Action E.5. Final event
Action E.6. Technical publications on the project
TASK E-ACTIONS

## Slide 15
Deliverables
D.E.1. Web portal of the project (EN)
D.E.2. E-brochure on the project in 4 European languages (EN, IT, SI, HR)
D.E.3. Video clip on the project (EN)
D.E.4. Layman’s report in 4 languages (EN, IT, SI; HR) in electronic format
D.E.5 Final Event on the post-earthquake damage assessment
(in the some place and date of the exercise)
D.E.6. At least 3 technical publications on the project
TASK e-DELIVERABLES
Task E. Dissemination

## Slide 16
Support ERRC and meet specific EUCP needs through the implementation of a dedicated multinational macro module on seismic safety assessment and short term countermeasures;
Contribution to the EU strategies: the macro-module will be registered in CECIS as additional resource;
Enhancement of the cross-border cooperation and exchange of best practices among MS in the field of disaster preparedness;
Increase of awareness and skills of civil protection professionals: about 100 experts will be trained on module technical activities and to face international emergencies;
Development of Standard Operating Procedures for the multinational module;
Development of specific information sheet for the requesting countries.
Expected results of the project
EXPECTED RESULTS

## Slide 17
Future actions mainly refer to:
the maintenance and standby arrangements for personnel, since the capability will be already implemented in terms of equipment and technology;
Additional training courses will be run in the future in order to always have the availability of highly trained human resources;
Registration in Cecis database
Follow up of the project
FOLLOW UP