## Slide 1: BE-AWARE Project
Bonn Agreement: Area-wide Assessment of Risk Evaluations
John Mouat, Deputy Secretary
BONN AGREEMENT

## Slide 2: Bonn Agreement Agreement for cooperation in dealing with pollution of the North Sea by oil and other harmful substances
Surveillance for threats of marine pollution
Development of common operational methods
Support in response operations
Sharing research and development
Carrying out joint exercises
Risk assessment

## Slide 3: Why do we need a risk Assessment in the Greater North Sea?
Increasing traffic and vessel size
Increased transports of oil and HNS
New maritime uses and activity
  Energy generation
  Ocean aquaculture
  Marine protected areas
Increased storminess

## Slide 4: Project Background
Bonn Agreement Ministerial Meeting 2010
  Dublin Declaration
  Bonn Agreement Action Plan (BAAP)
Risk Analysis Workshop, May 2011
No existing overview
Need to further develop on National risk assessments
Notes:   Hazard identification
  Risk modelling
  Lessons learned
  Awareness
  Multinational participation

## Slide 5
Regional risk of marine pollution
- evaluating resources (regional database)
- use levels (traffic and projected use)
- environmental sensitivity (most vulnerable)
Blue-print for disaster prevention (tested / validated)
- common tools
- collate information from existing studies
- regional overview
- sub-regional case study

## Slide 6: Project Structure
A) Project Management
Administrative and financial management
Information exchange and dissemination
B) Kick off Meeting
10-11th January, Delft, Netherlands
Partnership agreement, Communication plan
C) Regional Database
Data collection
Analysis of national risk assessments
Overview presentation

## Slide 7: Project Structure
D) Methodology
Development of a method note
Model modification
E) Area-wide traffic and use study
Present and projected traffic
F) Sensitivity Analysis
Environmental and socio-economic sensitivity
Maritime uses
Method seminar, Denmark, March 2012, tbc
Seminar to confirm common criteria, Belgium, Date tbc

## Slide 8
G) Risk Assessment Workshop
Workshop in Conjunction with Bonn 2012 (24-28th Sept)
H) Risk
Assessment
Validation of the risk assessment through application to a high risk area
J) Project Conference
I) Case Study
Quantitative risk assessment for mineral oil
Qualitative risk assessment for HNS
Identification of risk reduction measures
Review of final project results
Perspective on balance of resources
Dec 2013, [World Maritime University, Malmo, Sweden, tbc]

## Slide 9: Project partners
Coordinating Beneficiary:
Bonn Agreement
Associate Beneficiaries:
RBINS
MUMM
RWS
Noordzee
Admiral Danish Fleet HQ
Co-Financiers:
Norwegian Coastal Administration
Belgian Federal Public Service: Marine Environment Unit

## Slide 10: Project Funding
Total value : €540,800
BA Secretariat (CO) €40,000 in kind
Belgium (AB1) €2,000
Denmark (AB2) €15,000 + €31,300 in kind
Netherlands (AB3) €25,000
Belgium (ENV) €15,000
Norway €10,000
Co-financing by EU €402 500

## Slide 11: Timeline

## Slide 12: Reporting Schedule
Progress report 1 – July 2012
Interim Technical and Financial report – January 2013
Progress report 2 – July 2013
Final Technical and Financial report – March 2014

## Slide 13: Continuation
Joint sensitivity mapping and detailed analysis of impact
Modelling of a range of scenarios comprising additional risk reducing measures and response capabilities
Comprehensive HNS analysis
Enhanced preparedness in high risk areas

## Slide 14: Thank you www.bonnagreement.org 0044 (0)20 7439 5200