## Slide 1
Probabilistic TSUnami Hazard MAPS for the NEAM Region
Coordinated by
Istituto Nazionale di Geofisica e Vulcanologia (INGV)
Roberto Basili, PhD
roberto.basili@ingv.it
with the following partners
NGI | IPMA | GFZ | METU | UB | NOA | CNRST | INM
ECHO/SUB/2015/718568/PREV26
Prevention Project, Priority 3, External Budget Item

## Slide 2
Project funding and consortium
Total eligible cost: € 884,822.00
EC contribution: € 663,616.00 (75%)
Duration: 18 months
(01/01/2016 - 30/06/2017)
INGV | NGI | IPMA | GFZ | METU | UB | NOA | CNRST | INM
Basili R. Lorito S. Selva J. | Harbitz C.B. Løvholt F. | Baptista M. A. Matias L. Omira R. | Babeyko A. | Yalciner A. | Canals M. Lastras G. | Papadopoulos G. | El Mouraouah A. Ibenbrahim A. | Ben Abdallah S. Nmiri A.
Italy | Norway | Portugal | Germany | Turkey | Spain | Greece | Morocco | Tunisia
Member Sate | Participating State | Member Sate | Member Sate | Enlargement | Member Sate | Member Sate | Neighborhood Policy | Neighborhood Policy

## Slide 3
Area of activity: Tsunami hazard
Subject: Probabilistic tsunami hazard assessment (PTHA) and mapping
Tsunamis are low-frequency high-consequence events.
Probabilistic assessment of tsunami hazard is a strategic tool for tsunami and multi-risk mitigation.
Selection of dreadful historical earthquake-induced tsunamis in the NEAM region |  |  | 
Jul 21, 365 AD | Crete, Greece | M 8+ | largest destructive tsunami in the history of the Eastern Mediterranean Sea
Nov 1, 1755 | Lisbon, Portugal | M 8+ | large destructive tsunami in history of the Eastern Atlantic Sea
Dec 28, 1908 | Messina, Italy | M 7.1 | deadliest tsunami of the instrumental era in the central Mediterranean Sea
May 21, 2003 | Boumerdès, Algeria | M 6.8 | first tsunami of the new millennium in the Western Mediterranean Sea: a wake-up call?
earthquake and tsunami damage in the coastal area of Messina in 1908

## Slide 4
The project will develop the first homogeneous region-wide long-term Probabilistic earthquake-induced Tsunami Hazard Assessment (PTHA) for the coastlines of the North East Atlantic, the Mediterranean, and connected seas, and trigger a common tsunami-risk management strategy in the region.
These results will be achieved through:
realization of state-of-the-art PTHA with full uncertainty treatment;
review process with international experts;
production of the PTHA database and maps;
publicity of results through an awareness raising and education phase, and a capacity building phase.
The PTHA products can serve as a basis for future local and national PTHA efforts and be the first step to include tsunamis in multi-hazard risk assessments.
What will the project do?

## Slide 5
Examples of tsunami intensity metrics
Typical hazard curve at a site with uncertainty
Typical hazard maps representing the probability of exceedance of a given tsunami intensity threshold and average return period
What will the project do?
Hmax
Runup
Circled intensity metrics will be calculated by TSUMAPS-NEAM

## Slide 6
How will the project work?
ASTARTE: Assessment, STrategy And Risk Reduction for Tsunamis in Europe, EU FP7 project
SC: Steering Committee, formed by the TSUMAPS-NEAM Coordinator and all task leaders, plus ASTARTE PMB
OB: Observers’ Board, formed by end users and advisors
TSUMAPS-NEAM
ASTARTE
knowledge base
methods and data
SC
OB
TASKS
Actions
Products
EC
End Users
Stakeholders
CPAs
General public
...
UN-ISDR GAR15
National PTHAs
knowledge base
methods and data

## Slide 7
End Users and Advisors
SRB-RAS
(A. Zaytsev,
and E. Pelinovsky)
EWS-CARIBE
(C. von Hillebrandt-Andrade)
(E. Geist)
(M. Cocco)
(A. Annunziato)
IOC/UNESCO
(T. Aarup)
NEAMTWS-TNC
(M. Said)
NEAMTWS
cTSP (M. Erdik)
NEAMTWS candidate Tsunami Service Providers (embedded):
NOA (G. Papadopoulos)
IPMA (M.Miranda)
INGV (A. Michelini)
(A. Borrelli)
All these entities have formalized their expression of interest in the project.

## Slide 8
Deliverables and deadlines
Task ID | Task Title | Start Date | End Date | Actions | Deliverables | Task leaders
A | Management and Reporting to the Commission | 1 | 18 | A.1 Coordination A.2 Management and Reporting | D1. Six-Month Progress Report (M6) D2. Twelve-Month Progress Report (M12) D3. Final Report (M18) | INGV
B | Hazard Assessment | 1 | 11 | B.1 Earthquake Model B.2 Tsunami Modelling B.3 Probabilistic Model B.4 Hazard Analysis | D4. Online Tsunami Hazard Database (M11) D5. Tsunami Hazard and Probability Maps (M11) | INGV + IPMA
C | Review and Sanity Check | 4 | 16 | C.1 Best Practices C.2 Expert’s Review and Sanity Check C.3 Documentation | D6. Experts’ Review and Sanity Check (M9) D7. Methods and data Documentation (M16) | GFZ + NOA
D | Publicity | 1 | 18 | D.1 Awareness and Education D.2 Capacity Building | D8. Project Website (M1) D9. Awareness and Education Materials (M12) D10. Guidelines and Training Tools (M15) D11. Layman’s Report (M18) | METU

## Slide 9
Tentative dates and places for Major Events
Jan 1st, 2016 official start of the project
Jan 20th, 2016 KoM @Brussels
Feb, 2016 Technical KoM @Rome
17-22 Apr, 2016 join ASTARTE/GTM splinter meeting at EGU? @Vienna
Jun, 2016 technical review meeting @Athens
26-28 Sep, 2016 IOC-UNESCO ICG/NEAMTWS XIII @Bucharest
Oct, 2016 back-to-back meeting with ASTARTE @Lisbon
Dec, 2016 propose or join PTHA session at AGU? @San Francisco
Apr, 2017 propose or join PTHA session at EGU? @Vienna
Jun, 2017 final project meeting @Tunis

## Slide 10
Activities:
  Monitoring the actual usage of hazard products (online database, dissemination material, capacity building web tools).
  Maintenance, improvement, and update of the project website front-end, and the back-end database and software based on usage analysis and statistics, including feedback from end users.
Resources:
  Acquired equipment will be integrated with the existing institutional infrastructures to carry out review and update of hazard products.
  Permanent staff in participating institutions is already involved in long-term institutional programs devoted at tectonic and tsunami science, hazard analysis, and knowledge transfer to CPAs, the society, and educational programs for the general public.
  Support from entities that have expressed their interest in TSUMAPS-NEAM products (Italian NEAMTWS cTSP; EPOS; JRC; IOC/UNESCO).
Follow up