## Slide 1: CAFE Work Programme
Preparing the Thematic strategy on air pollution
October 2004
  First results of RAINS PaM scenarios and further advice from CAFE WG TSPA on PaMs
  TREMOVE ready for scenario runs/analysis. CBA starting.
  ASTA workshop in Gothenburg 25-27 October
November 2004 – discussions of results in CAFE WGs and SG. Possibly further advice. Drafting of CAFE integrated policy advice.
Jan/Feb 2005 – analysis of RAINS scenarios
March/April 2005 - finalisation of CAFE advice and draft TS. Including CBA and TREMOVE.
June 2005 - Adoption of Thematic Strategy by Commission

## Slide 2: Why NEC not as part of the Thematic Strategy?
Many Member States are updating their energy forecasts due to climate change policies
Need more time to improve emission factors in some areas
Need more time to finalise the development of the integrated assessment modelling framework
Enlargement amplifies the importance
No urgency to finalise this as the ceilings will be effective from 2010

## Slide 3: Preparing the NEC review: first thoughts
November 2004 – deadline for MS to submit revised energy baselines for NEC revision, new information on technologies
February 2005 – updating Integrated Assessment Model (IAM) for the NEC review
March to August 2005 – Consultations with Member States
November 2005 – Final stakeholder consultations on input
January 2006 – IAM operational for NEC revision
June 2006 – Commission proposal of revised NEC directive, including CBA