Timetable for FSS 2016

| Activity | Started | Finished |
| --- | --- | --- |
| Updating of the Statistical Farm Register | 02.01.2015 | 31.12.2017 |
| Development and approval of FSS 2016 documentation and methodology | 02.01.2015 | 31.05.2015 |
| Development of CAPI, CATI and CAWI (ISDAVS-CASIS) data input programme | 20.10.2015 | 01.07.2016 |
| Selection of agricultural holdings for FSS 2016 | 27.07.2016 | 08.08.2016 |
| Printing of FSS 2016 methodological materials | 03.08.2016 | 23.08.2016 |
| Press release “On progress of Farm Structure Survey 2016” |  | 19.08.2016 |
| Web data collection CAWI (ISDAVS-CASIS) | 22.08.2016 | 11.09.2016 |
| Training of LRATC interviewers | 19.09.2016 | 28.09.2016 |
| Press release “On progress of Farm Structure Survey 2016” |  | 05.10.2016 |
| Field work | 26.09.2016 | 20.12.2016 |
| Training of telephone interviewers |  | 29.09.2016 |
| Telephone interviews | 30.09.2016 | 20.12.2016 |
| Compilation, control, processing and analysis of data | 22.08.2016 | 28.04.2017 |
| Press release “First preliminary results of Farm Structure Survey 2016” |  | 27.04.2017 |
| Data control and processing, comparison with administrative data sources | 02.05.2017 | 29.09.2017 |
| Press release “Second preliminary results of Farm Structure Survey 2016” |  | 22.09.2017 |
| Adding information from administrative data sources to data file | 02.05.2017 | 30.09.2017 |
| Press release “Final results of Farm Structure Survey 2016” |  | 27.12.2017 |
| Development of summary tables and publication in data base | 06.10.2017 | 29.12.2017 |
| Development of Eurofarm data file, data transmission to Eurostat | 03.07.2017 | 29.12.2017 |
| Development of NMR Latvia 2016, transmission to Eurostat | 01.09.2017 | 29.12.2017 |
| Consultations with Eurostat for FSS 2016 data set and NMR | 01.12.2017 | 31.01.2018 |