## HOME
Annex for
Integrated Farm Statistics
This workbook provides additional information related to the quality report in the Metadata Handler.

## Timetable
TIMETABLE OF THE STATISTICAL PROCESS
Please indicate the year(s) in headings, in these columns. Add as many columns as relevant
Please indicate the months in sub-headings, in these columns. Add as many columns as relevant
| Activities Please modify/add/delete activities as relevant | Institutions / departments Please indicate the institutions / departments responsible for each activity
|  |  | 2022 | [6 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  |  | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1.0 | Objectives and requirements
1.1 | formation of workgroups for organisation of data collections | Istat - dcat | bar: 2022 Jun to 2022 Dec
1.2 | consultation of users | Istat - dcat | bar: 2022 Jun to 2022 Dec
1.3 | set-up objectives, target population, statistical units, classifications, precision requirements etc. | Istat - dcat | bar: 2022 Jun to 2022 Dec
1.4 | set-up organisation of the data collections (e.g. detailed timetable, specification of resources, costs estimation) | Istat - dcat | bar: 2022 Jun to 2022 Dec
1.5 | set-up legal frame | Istat - dcat / dgen | bar: 2023 Jan to 2023 Dec
2.0 | Design
2.1 | design of registry applications and connection with other administrative sources | Istat - dcat | bar: 2022 Sep to 2023 Apr
2.2 | building of sampling frame and sample selection | Istat - dcat / dcme | bar: 2023 Mar to 2023 Oct
2.3 | design of questionnaire | Istat - dcat | bar: 2023 Feb to 2023 May
2.4 | preparation of manuals for data collections and processing | Istat - dcat | bar: 2023 Feb to 2023 Sep
2.5 | design of data collection procedures | Istat - dcat / dcrd | bar: 2022 Sep to 2023 May
2.6 | design of data processing procedures | Istat - dcat / dcme | bar: 2022 Sep to 2023 May
3.0 | Data collection
3.1 | recruitment of interviewers | Istat - dcat / dcrd | bar: 2023 Oct to 2023 Dec
3.2 | training of interviewers and supervisors | Istat - dcat / dcrd | bar: 2023 Dec to 2024 Jan
3.3 | fieldwork | Istat - dcat / dcrd | bar: 2023 Dec to 2024 Apr
3.4 | evaluation and assessment of fieldwork | Istat - dcat / dcrd | bar: 2024 Jan to 2024 Apr
4.0 | Data processing and validation
4.1 | data validation (at record level) | Istat - dcat / dcme | bar: 2024 Feb to 2024 Jul
4.2 | data correction and imputation | Istat - dcat / dcme | bar: 2024 Feb to 2024 Jul
5.0 | Data compilation
5.1 | weight calculation and estimation | Istat - dcat / dcme | bar: 2024 Apr to 2025 Feb
5.2 | calculation of derived variables | Istat - dcat / dcme | bar: 2024 Feb to 2024 Dec
5.3 | calculation of quality indicators (e.g. non-response rates, relative standard errors, coverage errors, bias etc.) | Istat - dcat / dcme | bar: 2025 Feb to 2025 Mar
5.4 | aggregation and tabulation | Istat - dcat | bar: 2025 Feb to 2025 Mar
5.5 | validation of aggregated data | Istat - dcat | bar: 2025 Feb to 2025 Apr
6.0 | Data analysis
6.1 | data analysis | Istat - dcat | bar: 2024 Sep to 2025 Apr
7.0 | Data dissemination
7.1 | data dissemination | Istat - dcat / dcre | bar: 2025 Dec
| dcat: | Directorate for territory and environment
| dcme: | Directorate for methodology
| dcrd: | Directorate for data collection
| dcre: | Directorate for data diffusion
| dgen: | Directorate General

## Delays
DELAYS
Please describe serious delays in the timetable and reasons
If there are delays in the timetable, outline the reasons for the delays and the efforts to prevent the delays in the future. In particular, refer to delays in delivering the data to Eurostat.
Activity delayed | Reasons for delay | Efforts to prevent the delays in the future
Start of data collection | Administrative problems in recruiting enumerators | Anticipating and simplifying the administrative process
End of data collection | Consequence of start of data collection delay | Anticipating and simplifying the administrative process
Weight calculation and estimation | Calibration of estimates with updated benchmarks for 2023 | Anticipating the process