## Slide 1
Grant Agreement Preparation (GAP) – Description of the action
26 JANUARY 2022

## Slide 2: Outline
  Introduction to the Grant Agreement Preparation (GAP)
  The Description of the Action
  IT tools walkthrough

## Slide 3: Introduction to the Grant Agreement Preparation
Horizon Europe

## Slide 4: GAP: the process sequence
Preparatory work
(Before or at an early stage of grant preparation)
Evaluation
Grant preparation:
Interaction with beneficiaries
Drafting of GAP report
Internal approval
Award decision
Budgetary commitment
Grant signature
Pre-financing
5 months max
8 months max
Call deadline
Evaluation report ready
Info to beneficiaries: ESR (+ Invitation)
Grant signature
Accession forms
Comitology

## Slide 5: GAP: Timing
3 months max.
Invitation
+ ESR
Grant
signature
3 weeks
~1 week
2 weeks
submit
GA data
submit
GA data
(final)
remaining
issues
(if any)
consortium
consortium
PO
Grant agreement data (GA data)

## Slide 6: Structure of the Grant Agreement
Data sheet + core
grant
agreement
Annex 1,
description of the action
(project description)
Annex 2,
estimated
budget
Other Annexes
(e.g. annex 5 –
specific rules for HE)
Consortium
Project Officer
sum of
scientific/technical, budgetary, administrative, and legal information on your project
GRANT AGREEMENT DATA

## Slide 7: The Description of the Action
Horizon Europe

## Slide 8: Description of the Action
  The Description of the Action (DoA) is Annex 1 to the Grant Agreement
  It contains the details of how the project will be carried out.
  It consists of 2 parts, which must be generated from the submitted proposal:
    Part A contains structured tables with project information. It is generated by the IT system, based on the information you enter into the Portal Grant Preparation screens. It is partially pre-filled with proposal data.
    Part B is a narrative description on the work to be carried out. It must closely follow the proposal part B and must be uploaded as a PDF.
Coordinator will be able to download the DoA template (instructions) from the Portal at the time of grant preparation invitation.

## Slide 9: Description of the Action – Part A
  Part A of the Description of the Action (DoA) must be completed directly on the Portal Grant Preparation screens.
  It will include:
  COVER PAGE
  TABLE OF CONTENTS
  Project summary (automated – based on proposal abstract)
  List of participants (automated – based on proposal information)
  List of work packages (based on proposal table 3.1b)
  Staff effort (based on proposal table 3.1f)
  List of deliverables (based on proposal table 3.1c)
  List of milestones (based on proposal table 3.1d)
  List of critical risks (based on proposal table 3.1e)
All changes need to be discussed and agreed with the EU Project Officer. Substantial changes to the proposal are NOT allowed.

## Slide 10: Description of the Action – Part B
Instructions:
  START from Part B of your proposal. Use the version that was submitted for evaluation.
  REMOVE the cover page, if any.
  DELETE the header, if any.
  REPLACE the footer with the following information ‘[Proposal number] [Proposal acronym] – Part B – [Page number (starting at 1 for Part B)]’.
  REMOVE the list of participants. This is included in Part A.
  REMOVE tables 3.1a (list of work packages), 3.1b (work packages descriptions), 3.1c (list of deliverables), 3.1d (list of milestones), 3.1e (critical risks for implementation) and 3.1f (summary of staff effort) from section 3.1 (they are encoded in the screens and included in Part A). Keep tables 3.1g, 3.1h, 3.1i and 3.1j (and any other table linked to specific types of actions).
  CREATE a section 4 ‘ethics self-assessment’ and copy into this section the ethics self-assessment you included in the proposal Part A.
  ADD a table with the history of changes. Specify all changes compared to your proposal. Changes should be described concisely. You do not need to include minor changes that do not modify the substance of the DoA (e.g. correction of spelling and grammar, changes in formatting).
  ADD a table of contents with page numbers (or update the existing table of contents).
Use the submitted version of the proposal. All changes need to be discussed and agreed with the EU Project Officer. Substantial changes to the proposal are NOT allowed.

## Slide 11: Other points to pay attention to
  Ethics review and security scrutiny
  The proposals are subject to an ethics review and may be subject to security scrutiny.
  The results of the ethics review and/or a security scrutiny must be implemented in the grant agreement
  'Ethics requirements' are binding, they must be entered by the PO in Part A (DoA)
  Coordinator needs to update the ethics section in Part B (DoA) to ensure that any 'ethics requirements' are met
  There may be 'ethics requirements' that need to be met before the grant can be signed
  Similarly for security scrutiny
  One final point…
  Avoid repetition of information
    E.g., no duplication between work plan tables (Part A) and free text (Part B)
    All information should appear in one, findable, place only

## Slide 12: IT tools walkthrough
Horizon Europe

## Slide 13: IT system for grant management

## Slide 14: Grant management service

## Slide 15: Beneficiaries

## Slide 16: Partner summary
  Coordinator/beneficiary Partner Summary is automatically listed after receiving the invitation letter.
  The department needs to be added (mandatory for all beneficiaries, except for Affiliated Entities)
  For HE calls (from 2022 onwards) having a Gender Equality Plan is necessary (for public bodies, research organizations and higher education institutions) before signing the GA (existence of the plan has to be declared in the portal organizational data)

## Slide 17: Financial information
  Coordinator/beneficiary financial Information is automatically listed after receiving the invitation letter (from proposal).

## Slide 18: Project representatives
  If no Project Representatives are listed, please complete in the roles management section of the Funding & Tenders Portal.
  Check all information and update, if necessary, in the roles management section of the Funding & Tenders Portal.
  Both Coordinators and beneficiaries should, as soon as they have been invited, nominate in the Funding & Tenders Portal, their Legal Entity Appointed Representative (LEAR) and Project Legal Signatory (PLSIGN). Once this has been done, the PLSIGN who will appear in the Grant Agreement has to be selected in this screen. Please note that all other PLSIGNs can sign the Grant Agreement.

## Slide 19: Affiliated entities

## Slide 20: Associated partners
  Data prefilled with proposal information
  Associated partners do not sign the grant agreement and cannot declare costs
  They will be allowed to be WP leaders (currently not possible)
  Budget table in GA (Annex 2) will not include any information of the budget of AP. Information is included in the proposal and if needed, some information can also be included in DoA - part B
  Coordinator will be able to enter researchers in the researcher table for AP

## Slide 21: Back account (coo only)
  Select your bank account from the list of accounts already registered in the Participant Register. For more information about how to register a bank account in the Participant Register, please click here.

## Slide 22: Researchers
  Listing the researchers funded by the action is obligatory under HE; each beneficiary enters their own
  Option A: Complete manually all the mandatory data fields
  Option B: Retrieve the researcher's personal data (the ones made public, using the information provided by the researcher in the My Person Profile section of the F&T Portal)
  Removal of researchers listed in proposal only conditional (subject to EU agreement)

## Slide 23: Work Packages
  The Project Work Packages are not automatically listed after receiving the invitation letter.
  Complete all necessary work packages
  You can change the order of the work packages by dragging and dropping.

## Slide 24: Deliverables
  Deliverables are not automatically listed
  All deliverables in proposal need to be included with the same details
  Select appropriate Dissemination status (Public, Sensitive (limited under conditions in GA), EU classified (EU-restricted/EU-confidential/EU-secret).

## Slide 25: Milestones
  Milestones are not automatically listed
  All milestones in proposal need to be included with the same details

## Slide 26: Critical risks
  Critical risks are not automatically listed
  All critical risks in proposal need to be included with the same details

## Slide 27: Ethics
  Ethics screen is available as read only
  Before a final Opinion is encoded by Ethics experts in the Ethics evaluation process, at times, additional information may be requested from the applicant.
  The Consortium or its representative has to upload the requested information in Grant Management application in the Funding & Tenders Portal, under section ‘Additional Information request’

## Slide 28: Security (NEW!)

## Slide 29: Part B of DoA
  Check instructions on slide 10 of this presentation
  Before uploading the part B, please remove the cover pages, the list of participants and add a history of changes. Changes need to be described concisely. Please add also a table of contents and page numbers.
  Please remove also, deliverables, milestones, risks and work packages as these are included in part A
  After creating the pdf, you may upload in the documents section
  Avoid repetition of information

## Slide 30: For more information…
  … check recorded webinars:
  ‘How to prepare a successful proposal in Horizon Europe’ (24 March 2021). See recorded session here.
  ‘A successful proposal for Horizon Europe: Scientific-technical excellence is key, but don’t forget the other aspects’ (21 April 2021). Recorded session
  ‘The Funding & Tenders Portal for beginners’ (27 May 2021). Recorded session
  ‘All you need to know on D&E under Horizon Europe’ (9 June 2021). Recorded session
  ‘How to prepare a successful innovation procurement proposal for Horizon Europe’ (22 June 2021). Recorded session
  ‘Horizon Europe: key changes to the Ethics Appraisal Process’ (18 July 2021). Recorded session
  R&I Days 2021: workshop on ‘Tips and tricks while writing your HE proposal’ (23 June 2021). Recorded session
  Thematic info-days per cluster (June – July 2021). Event page
Check the news section of the F&T Portal regularly: https://ec.europa.eu/info/funding-tenders/opportunities/portal/screen/home

## Slide 31
Thank you!
# HorizonEU
http://ec.europa.eu/horizon-europe